## Construction Gantt Chart
Gantt Chart
Project Name: ShiftSmart
Task Name | Start (Date) | End (Date) | Duration (Days) | Priority | Percentage of Completion
Project Initiation | 2024-08-18 | 2024-09-17 | 30 | High | 100%
Requirements Gathering & Analysis | 2024-09-17 | 2024-10-08 | 21 | High | 90%
System Design & Architecture | 2024-10-08 | 2024-10-29 | 21 | High | 0%
Development of Core Features | 2024-10-29 | 2024-12-28 | 60 | Medium | 0%
Integration with External Systems | 2024-12-28 | 2025-01-27 | 30 | High | 0%
Testing and Quality Assurance | 2025-01-27 | 2025-02-26 | 30 | High | 0%
User Training and Documentation | 2025-02-26 | 2025-03-13 | 15 | High | 0%
Deployment and Final Sign-Off | 2025-03-13 | 2025-03-28 | 15 | Medium | 0%

## Manufacturing Gantt Chart
Gantt Chart Template for Manufacturing
Project Name:
Task Name | Start (Date) | End (Date) | Duration (Days) | Priority | Percentage of Completion
Initial meetings | 2025-02-01 | 2025-02-05 | 4 | High | 100%
Define project scope | 2025-02-02 | 2025-02-08 | 6 | High | 100%
Design specifications | 2025-02-10 | 2025-02-25 | 15 | High | 50%
Design documents | 2025-02-25 | 2025-03-10 | 13 | Medium | 0%
Design review | 2025-03-12 | 2025-03-23 | 11 | Medium | 0%
Identify suppliers | 2025-03-24 | 2025-03-30 | 6 | Medium | 0%
Order materials | 2025-04-02 | 2025-04-20 | 18 | High | 0%
Set up production line | 2025-04-02 | 2025-04-19 | 17 | High | 0%
Prototype production | 2025-04-16 | 2025-05-15 | 29 | High | 0%
Prototype testing | 2025-05-16 | 2025-05-30 | 14 | Medium | 0%
Production phase | 2025-06-01 | 2025-07-10 | 39 | High | 0%
Product inspection | 2025-07-11 | 2025-07-30 | 19 | High | 0%
Package final products | 2025-08-01 | 2025-08-06 | 5 | Medium | 0%
Distribution logistics | 2025-08-07 | 2025-08-18 | 11 | High | 0%
Deliver products to client | 2025-08-20 | 2025-08-25 | 5 | High | 0%
Obtain client approval | 2025-09-01 | 2025-09-07 | 6 | High | 0%
Post-project review | 2025-09-08 | 2025-09-10 | 2 | Medium | 0%

## Software Dev Gantt Chart
Gantt Chart Template for Software Development
Project Name:
Task Name | Start (Date) | End (Date) | Duration (Days) | Priority | Percentage of Completion
Project requirements | 2025-01-04 | 2025-01-10 | 6 | High | 100%
Define scope | 2025-01-11 | 2025-01-19 | 8 | High | 100%
Risk management plan | 2025-01-21 | 2025-02-10 | 20 | Medium | 0%
UI prototypes | 2025-02-12 | 2025-02-20 | 8 | Medium | 0%
Technical architecture | 2025-02-21 | 2025-03-05 | 12 | High | 0%
Design approval | 2025-03-06 | 2025-03-15 | 9 | Medium | 0%
Development environment | 2025-03-16 | 2025-03-30 | 14 | High | 0%
Front-end development | 2025-04-01 | 2025-04-25 | 24 | High | 0%
Back-end development | 2025-04-26 | 2025-05-25 | 29 | High | 0%
Database setup | 2025-06-01 | 2025-06-15 | 14 | Medium | 0%
API development | 2025-06-16 | 2025-06-30 | 14 | Medium | 0%
Unit testing | 2025-07-02 | 2025-07-30 | 28 | Medium | 0%
User acceptance test | 2025-08-01 | 2025-08-15 | 14 | High | 0%
Bug fixes | 2025-08-16 | 2025-08-30 | 14 | High | 0%
Deployment environment | 2025-09-01 | 2025-09-15 | 14 | High | 0%
Go-live and release | 2025-09-16 | 2025-10-10 | 24 | High | 0%
Performance tracking | 2025-10-11 | 2025-10-31 | 20 | Medium | 0%
Final project review | 2025-11-02 | 2025-11-08 | 6 | Medium | 0%

## Service Delivery Gantt Chart
Gantt Chart Template for Professional Services Teams
Project Name:
Task Name | Start (Date) | End (Date) | Duration (Days) | Priority | Percentage of Completion
PMO service proposal | 2025-02-03 | 2025-02-15 | 12 | High | 100%
Service agreement | 2025-02-16 | 2025-03-02 | 14 | High | 100%
PMO roadmap | 2025-03-03 | 2025-03-15 | 12 | High | 75%
Assign consultants | 2025-03-16 | 2025-03-30 | 14 | Medium | 50%
Resource planning | 2025-04-01 | 2025-04-15 | 14 | Medium | 0%
Risk assessment | 2025-04-16 | 2025-04-28 | 12 | Medium | 0%
Kickoff meeting with client | 2025-05-01 | 2025-05-02 | 1 | High | 0%
Review project portfolio | 2025-05-03 | 2025-05-12 | 9 | High | 0%
Reporting protocols | 2025-05-15 | 2025-05-30 | 15 | Medium | 0%
Gap analysis | 2025-06-02 | 2025-06-12 | 10 | High | 0%
Improvement plan | 2025-06-15 | 2025-06-28 | 13 | High | 0%
Change management process | 2025-07-01 | 2025-07-26 | 25 | High | 0%
Staff training | 2025-07-28 | 2025-08-20 | 23 | Medium | 0%
Monitor improvements | 2025-08-21 | 2025-09-05 | 15 | Medium | 0%
KPI reports | 2025-09-06 | 2025-09-15 | 9 | Medium | 0%
Final report | 2025-09-16 | 2025-09-20 | 4 | Medium | 0%
Post-project review | 2025-09-21 | 2025-09-26 | 5 | Medium | 0%
Task Name | Start Date | End Date | Duration (Days) | Priority Level | % of Completion
Project Initiation | 2024-02-01 | 2024-02-10 | 10 | High | 100%
Initial client meeting to define scope | 2024-02-01 | 2024-02-02 | 2 | High | 100%
Draft and finalize PMO service proposal | 2024-02-03 | 2024-02-05 | 3 | High | 100%
Contract and service agreement signing | 2024-02-06 | 2024-02-10 | 5 | High | 100%
Planning Phase | 2024-02-11 | 2024-02-28 | 18 | High | 50%
Develop PMO roadmap and service deliverables | 2024-02-11 | 2024-02-18 | 8 | High | 75%
Assign consultants and team roles | 2024-02-19 | 2024-02-21 | 3 | Medium | 50%
Resource planning and allocation | 2024-02-22 | 2024-02-25 | 4 | Medium | 0%
Risk assessment and mitigation planning | 2024-02-26 | 2024-02-28 | 3 | Medium | 0%
Consulting Kickoff | 2024-03-01 | 2024-03-05 | 5 | High | 0%
Kickoff meeting with client | 2024-03-01 | 2024-03-01 | 1 | High | 0%
Review project portfolio and current processes | 2024-03-02 | 2024-03-04 | 3 | High | 0%
Establish communication and reporting protocols | 2024-03-05 | 2024-03-05 | 1 | Medium | 0%
Process Improvement Recommendations | 2024-03-06 | 2024-04-10 | 36 | High | 0%
Conduct gap analysis and process assessment | 2024-03-06 | 2024-03-20 | 15 | High | 0%
Provide recommendations and improvement plan | 2024-03-21 | 2024-04-01 | 12 | High | 0%
Review recommendations with client | 2024-04-02 | 2024-04-05 | 4 | Medium | 0%
Finalize and approve improvement roadmap | 2024-04-06 | 2024-04-10 | 5 | High | 0%
Implementation Support | 2024-04-11 | 2024-06-30 | 80 | High | 0%
Assign teams to implement improvements | 2024-04-11 | 2024-04-15 | 5 | Medium | 0%
Oversee change management process | 2024-04-16 | 2024-06-01 | 46 | High | 0%
Support ongoing PMO activities | 2024-04-16 | 2024-06-30 | 75 | High | 0%
Provide coaching and staff training | 2024-06-02 | 2024-06-30 | 29 | Medium | 0%
Monitoring & Reporting | 2024-07-01 | 2024-08-01 | 32 | Medium | 0%
Ongoing monitoring of improvements | 2024-07-01 | 2024-07-25 | 25 | Medium | 0%
Produce monthly status and KPI reports | 2024-07-05 | 2024-08-01 | 27 | Medium | 0%
Project Closeout | 2024-08-02 | 2024-08-10 | 9 | Medium | 0%
Final report and project review | 2024-08-02 | 2024-08-06 | 5 | Medium | 0%
Post-project review and lessons learned | 2024-08-07 | 2024-08-10 | 4 | Medium | 0%

## Event Planning Gantt Chart
Gantt Chart Template for Event Planning
Project Name:
Task Name | Start (Date) | End (Date) | Duration (Days) | Priority | Percentage of Completion
Define event scope | 2024-10-15 | 2024-11-03 | 19 | High | 100%
Event budgeting | 2024-11-06 | 2024-11-20 | 14 | High | 100%
Secure speakers | 2024-11-21 | 2024-12-05 | 14 | High | 75%
Book vendors | 2024-12-06 | 2024-12-20 | 14 | Medium | 50%
Event branding materials | 2024-12-01 | 2024-12-20 | 19 | Medium | 50%
Send invitations | 2024-12-10 | 2025-01-15 | 36 | Medium | 25%
Venue setup | 2025-01-16 | 2025-02-05 | 20 | Medium | 50%
Speaker schedule | 2025-01-25 | 2025-02-15 | 21 | High | 25%
Speaker transportation | 2025-02-16 | 2025-03-01 | 13 | Medium | 0%
Marketing campaign | 2025-01-01 | 2025-02-15 | 45 | High | 50%
Promotional ads | 2025-02-16 | 2025-03-15 | 27 | Medium | 25%
Track registrations | 2025-03-16 | 2025-03-30 | 14 | High | 25%
Set up venue | 2025-04-01 | 2025-04-16 | 15 | High | 0%
Attendee check-in | 2025-04-20 | 2025-04-25 | 5 | High | 0%
Conference workshops | 2025-04-30 | 2025-05-10 | 10 | High | 0%
Event success metrics | 2025-05-15 | 2025-05-25 | 10 | Medium | 0%
Post-event survey | 2025-05-26 | 2025-06-05 | 10 | Medium | 0%
Final report | 2025-06-06 | 2025-06-15 | 9 | Medium | 0%
Task Name | Start Date | End Date | Duration (Days) | Priority Level | % of Completion
Event Initiation | 2024-11-01 | 2024-11-10 | 10 | High | 100%
Define event scope and objectives | 2024-11-01 | 2024-11-03 | 3 | High | 100%
Confirm event date and location | 2024-11-04 | 2024-11-05 | 2 | High | 100%
Create event budget and secure approval | 2024-11-06 | 2024-11-10 | 5 | High | 100%
Planning Phase | 2024-11-11 | 2025-01-15 | 66 | High | 50%
Secure keynote speakers and panelists | 2024-11-11 | 2024-12-05 | 25 | High | 75%
Book caterers, audio-visual (AV) setup, and vendors | 2024-12-06 | 2024-12-20 | 15 | Medium | 50%
Design event branding and materials | 2024-12-01 | 2024-12-20 | 20 | Medium | 50%
Send event invitations and open registration | 2024-12-10 | 2025-01-15 | 36 | Medium | 25%
Logistics and Coordination | 2025-01-16 | 2025-03-10 | 54 | High | 25%
Finalize venue setup and seating arrangement | 2025-01-16 | 2025-02-05 | 21 | Medium | 50%
Finalize speaker schedule and sessions | 2025-01-25 | 2025-02-15 | 21 | High | 25%
Coordinate transportation and accommodation for speakers | 2025-02-16 | 2025-03-01 | 14 | Medium | 0%
Reconfirm with all vendors and sponsors | 2025-02-20 | 2025-03-10 | 19 | Medium | 0%
Event Marketing and Outreach | 2025-01-01 | 2025-03-15 | 74 | High | 25%
Launch marketing campaign (email, social media) | 2025-01-01 | 2025-02-15 | 46 | High | 50%
Run promotional ads and outreach activities | 2025-02-16 | 2025-03-15 | 28 | Medium | 25%
Track registrations and manage attendee queries | 2025-01-10 | 2025-03-20 | 71 | High | 25%
Event Execution | 2025-03-16 | 2025-03-20 | 5 | High | 0%
Set up venue and AV equipment | 2025-03-16 | 2025-03-17 | 2 | High | 0%
Registration and attendee check-in | 2025-03-18 | 2025-03-18 | 1 | High | 0%
Manage conference sessions and workshops | 2025-03-18 | 2025-03-19 | 2 | High | 0%
Provide attendee support and networking spaces | 2025-03-18 | 2025-03-19 | 2 | Medium | 0%
Conference closing ceremony and feedback collection | 2025-03-20 | 2025-03-20 | 1 | High | 0%
Post-Event Wrap-up | 2025-03-21 | 2025-03-31 | 11 | Medium | 0%
Review event success and metrics | 2025-03-21 | 2025-03-25 | 5 | Medium | 0%
Post-event survey and feedback analysis | 2025-03-26 | 2025-03-31 | 6 | Medium | 0%
Final report and lessons learned | 2025-03-26 | 2025-03-31 | 6 | Medium | 0%

## How To Use This Template
How To Use This Template
This Gantt chart template can be used to make a project schedule by following these steps:
1. List Project Tasks
Once you've identified the tasks that make up a project, begin listing them in the "Task name" column. The first project task should be at the top.
2. Set Start and End Dates for Each Task
Estimate the duration of each task and define their start and end dates using the "Start date" and "End date" columns.
3. Specify the Priority Level of Tasks
Not all project tasks are equal. Some of them have a special importance for the completion of the project on time and under budget. By default the template uses three priority levels, low, medium and high, but you may customize them as needed.
4. Track the Percentage of Completion of Tasks
After making a project schedule, the Gantt chart template serves as a project tracking tool that can be used to track the progress of each task using the "Percentage of Completion" column